## Process list
S. No. | Business Process | Module | Logic Shared | Bot development Status | Start Date | End Date | RPA Developer | Tester | Testing | Remaks
0 | Login to SAP | Common
1 | Create NB Standard Purchase Order | MM | Yes | In Process | 02.09.2021 | 02.10.2021 02.11.2021 | Abhinav | Divya
2 | Process order end to end | PP | Yes | In Process | 02.09.2021 | 02.10.2021 02.11.2021 | Tushar | Puneet
3 | GID_Inernational Contract_Contact-to-Cash | SD | Yes |  | 02.11.2021 | 02.12.2021 | Mojassar | Aravind
4 | GID_Domestic_Contract_Order-to-Cash | SD | Yes |  | 02.11.2021 | 02.12.2021 | Mojassar | Aravind
5 | GID_Spot_Order | SD | [5 empty] | Aravind
6 | GID_G2_Credit_Memo | SD | Yes |  | 02.11.2021 | 02.12.2021 | Tushar | Aravind
7 | GID_L2_Debit_Memo | SD | [5 empty] | Aravind
8 | Internal Order | FICO | [5 empty] | Dev
9 | Park GL Account Document | FICO | [5 empty] | Dev
10 | Recurring Entry | FICO | [5 empty] | Dev
11 | Create UD STO | MM | [5 empty] | Divya
12 | Create UB STO | MM | Yes |  | 02.11.2021 | 02.12.2021 | Abhinav | Divya
13 | Create ZXS STO to move from Plant 1000 | MM | [5 empty] | Divya
14 | Create Framework Purchase Order | MM | [5 empty] | Divya
15 | Create ZGIS STO going from Plant 1000 (Grower Location)to 1000 1010 | MM | [5 empty] | Divya
16 | Rework Process Order | PP | [5 empty] | Puneet
17 | Standard Process Order - without QM | PP | [5 empty] | Puneet
18 | Return process on sales order (non HU managed location) | WM | [5 empty] | Puneet / Aravind / Divya
19
20

## P_13
Step # | Description | SAP Transaction | Input Data Field | Input Data Value | Expected Result | Actual Result | Step Complete (Yes/No) | Pass / Fail
1 | Create Purchase Order | ME21N | Document Type | ZXS Quality/Blocked STO | Quality/Blocked STO created under the number 9300012038 |  | Yes | Pass
|  |  | Supplier Plant | 1235
|  |  | Purchase Organisation | 1000
|  |  | Purchasing Group | 999
|  |  | Company Code | 1000
|  |  | Material Code | 04426
|  |  | PO Quantity | 1
|  |  | Plant | 1000
|  |  | Storage Location | 1030
|  |  | issue st loc. | 1030
Shipping Tab -
|  |  | Shiping Condition | ZC
|  |  | Route | SMOIL6
Deliver tab
Quality Ispection
Quality Ispection
|  |  | Check | X
2 | Outbound Delivery Document No. | ME23N | From Purchase order Tab | X | Outbound Delivery 86212840 Created |  | No | Fail
3 | Change Outbound Delivery | VL02N | Picking Tab -
|  |  | Picking Quantity | 2000
|  |  | Batch No. | 1000194786
3 | Change Inbound Delivery | VL32N | Date of Manufacturing | 2021-02-05 | Goods receipt for inbound delivery 183369737 posted (material document 5002885776)
|  |  | Packaging Materials | HUBDGLP1

## Process 12
Step # | Description | SAP Transaction | Input Data Field | Input Data Value | Expected Result | Actual Result | Step Complete (Yes/No) | Pass / Fail
1 | Create Purchase Order | ME21N | Document Type | ZXS Quality/Blocked STO | Quality/Blocked STO created under the number 9300012038 |  | Yes | Pass
|  |  | Supplier Plant | 1235
|  |  | Purchase Organisation | 1000
|  |  | Purchasing Group | 999
|  |  | Company Code | 1000
|  |  | Material Code | 04426
|  |  | PO Quantity | 2000
|  |  | Plant | 1000
|  |  | Storage Location | 1030
|  |  | issue st loc. | 1030
Shipping Tab -
|  |  | Shiping Condition | ZC
|  |  | Route | SMOIL6
Deliver tab
Quality Ispection
Quality Ispection
|  |  | Check | X
2 | Create Outbound Delivery | VL10B | From Purchase order Tab | X | Outbound Delivery 86212840 Created |  | No | Fail
3 | Change Outbound Delivery | VL02N | Picking Tab -
|  |  | Picking Quantity | 2000
|  |  | Batch No. | 1000194786
3 | Change Inbound Delivery | VL32N | Date of Manufacturing | 2021-02-05 | Goods receipt for inbound delivery 183369737 posted (material document 5002885776)
|  |  | Packaging Materials | HUBDGLP1

## Process 6
Step # | Description | SAP Transaction | Input Data Field | Input Data Value | Expected Result | Actual Result | Step Complete (Yes/No) | Pass / Fail
1 | Create Credit Memo Request | VA01 | Document Type | CR | Credit memo request 60011975 has been saved. |  | Yes | Pass
|  |  | Sales Orgniazation | 1000
|  |  | Distribution Channel | 10
|  |  | Division | 10
Billing Document
|  |  | Order Reason | 101
2 | Create Credit Memo | VF01 | Credit memo request no. | From Step 1 | Document 90241750 has been saved. |  | Yes | Pass

## Process 4
Step # | Description | SAP Transaction | Input Data Field | Input Data Value | Expected Result | Actual Result | Step Complete (Yes/No) | Pass / Fail
1 | Create Quantity Contract | VA41 | Document Type | CQ | Quantity Contract 40009309 has been saved. |  | Yes | Pass
|  |  | Sales Orgniazation | 1000
|  |  | Distribution Channel | 10
|  |  | Division | 10
|  |  | Plant | 1272
|  |  | Sold to Party | 101301
|  |  | Ship to Party | 101301
|  |  | Valid From date | Todays's date
|  |  | Valid To date | Contract end date
|  |  | Material | 10539
|  |  | Quantity | 2
|  |  | Condition Type | ZPR0
|  |  | Amount | 2.35
|  |  | Currency | USD
|  |  | Amount | 2.35
|  |  | Text | Bot Testing
2 | Create Sales Order | VA01 | Document Type | OR | Standard Order 220841 has been saved. |  | Yes | Pass
|  |  | Sales Orgniazation | 1000
|  |  | Distribution Channel | 10
|  |  | Division | 10
|  |  | Division | 10
|  |  | Contract No. | From Step 1
|  |  | Releasing Partner | Sold to Party (101301)
|  |  | Quantity | 1
3 | Release Credit Block | VKM1 | Credit Account (Payer) | From Step 2 (200014) | 220841 has been released. |  | Yes | Pass
4 | Create Delivery | VL01N | Shipping Point | 1272 | Delivery 80334232 has been saved. |  | Yes | Pass
|  |  | Selection date | Todays's date
|  |  | Order | From step 2
|  |  | Picking Quantity | 1
|  |  | Contract No. | From Step 1
Batch
Handling Unit
5 | Create Invoice | VF01 | Delivery No. | From Step 4 | Document 90241746 has been saved. |  | Yes | Pass

## Open Items
Yes | In Process | Pass
No | Complete | Fail
|  | S.No. | Open Issue | Remarks | Github Access details
|  | 1 | Licence for UI Path Test Suite | To be checked with Amit | Puneet Kalra | kalrapuneet
|  | 2 | GitHub Access for functional team |  | Dev Rishi | devarora11
|  | 3 | Teams Group access for Mojassar |  | Divya CHopra
|  | 4 | Divya's Github Access |  | Tushar
Abhinav
[5 empty] | Aravind | aravindrawat

## Process 1
Step # | Description | SAP Transaction | Input Data Field | Input Data Value | Expected Result | Actual Result | Step Complete (Yes/No) | Pass / Fail
1 | Create Purchase Order | ME21N | Document Type | NB Standard PO | Standard PO 4500087236 created |  | Yes | Pass
|  |  | Supplier Code | 300003
|  |  | Purchase Organisation | 1000
|  |  | Purchasing Group | 103
|  |  | Company Code | 1000
|  |  | Material Code | P35035
|  |  | PO Quantity | 1000
|  |  | Plant | 1000
|  |  | Storage Location | 1030
|  |  | Check | X
2 | Inbound Delivery Document No. | ME23N | From Confirmation Tab | X | Inbound Delivery 183369692 |  | No | Fail
3 | Change Inbound Delivery | VL32N | Batch No. | Test9875 | Material Document 5002885751
|  |  | Date of Manufacturing | 2021-02-05
|  |  | Packaging Materials | HUBDGLP1
4 | Change Inspection Lot | QA32

## Process 3
Step # | Description | SAP Transaction | Input Data Field | Input Data Value | Expected Result | Actual Result | Step Complete (Yes/No) | Pass / Fail
1 | Create Quantity Contract | VA41 | Document Type | CQ | Quantity Contract 40009305 has been saved. |  | Yes | Pass
|  |  | Sales Orgniazation | 1000
|  |  | Distribution Channel | 10
|  |  | Division | 10
|  |  | Plant | 1272
|  |  | Sold to Party | 101215
|  |  | Ship to Party | 101215
|  |  | Valid From date | Todays's date
|  |  | Valid To date | Contract end date
|  |  | Material | 8470
|  |  | Quantity | 60
|  |  | Condition Type | ZPR0
|  |  | Amount | 2.35
|  |  | Currency | USD
|  |  | Amount | 2.35
2 | Create Sales Order | VA01 | Document Type | OR | Standard Order 220834 has been saved. |  | Yes | Pass
|  |  | Sales Orgniazation | 1000
|  |  | Distribution Channel | 10
|  |  | Division | 10
|  |  | Division | 10
|  |  | Contract No. | From Step 1
|  |  | Releasing Partner | Sold to Party (101215)
|  |  | Quantity | 60
3 | Create Delivery | VL01N | Shipping Point | 1272 | Delivery 80334232 has been saved. |  | Yes | Pass
|  |  | Selection date | Todays's date
|  |  | Order | From step 2
|  |  | Picking Quantity | 60
|  |  | Contract No. | From Step 1
Batch
Handling Unit
4 | Create Invoice | VF01 | Delivery No. | From Step 3 | Document 90241746 has been saved. |  | Yes | Pass

## Process 2
| Description | SAP Transaction | Input Data Field | Input Data Value | Expected Result | Actual Result | Step Complete (Yes/No) | Pass / Fail
1 | Create Process Order | COR1 | Material Number | 11066 | Process Order XXXX created |  | Yes | Pass
|  |  | Production Plant | 1000
|  |  | Process Order Type | YBM2
|  |  | Total Qty | 10
|  |  | Start Date | Current Date
2 | Goods Receipt against Process Order | MIGO | Item Ok | X
|  |  | Qty | 10
|  |  | Date of Manufacture | Current Date
3 | Transfer Stock to Resource | LS24 | Warehouse No. | A01
|  |  | Material Number | 01578
|  |  | Plant | 1000
3.1 | Transfer Stock to Resource | LM01 | Override | 7453
4 | Goods Issue against Process Order | LB13 | Warehouse No. | A01
|  |  | Reqiorement No. | P, Process Order
| Confirm Transfer Order | LT12
5 | Confirm Process Order | COR6 | Process Order | From Previous steps